## Sheet1
Bird Species Detection using Deep Learning
Date | Task/Work | Expected Work | Updates by Megh | Updates by Konark | Status | Expected Work
2025-09-15 | Project Proposal Submittion to Prof. Maitrik Shah | Dataset Exploration | Completed review of 5 papers | Completed review of 5 papers | Completed
2025-09-16 | 1. Dataset Download and Upload on Drive 2. Species selection 3. Data Segregation (Based on the updated list of species) | Data Segregation (Based on the updated list of species) | 1. Updated classes.txt file manually 2. Updated image_class_labels.txt file in the dataset as per the selected species using pandas functions [Conversion of the txt files to csv files and making updates through functions, and then again converting the csv back to txt file] 3. Updated images.txt file manually 4. Deleted folders for the species which are not considered | Selected Specific Species from the dataset to reduce training load. | In Progress | Get the range of the number of species for all the species considered/non-considered